## Slide 1
Monthly Portfolio Health Review
Professional Services — Client Program Portfolio
Reporting Period: July 2, 2026 – July 2, 2026 | Prepared for: Executive Sponsor Review

## Slide 2
Portfolio Snapshot
Where the portfolio stands as of the latest reporting week
Chart: 
| Red | Amber | Green
Projects | 1 | 1 | 0
2
Projects in Portfolio
0
Declining This Month
0
Recovering This Month
2 of 2 project-weeks
Weeks w/ Negative Client Sentiment

## Slide 3
Trend Analysis: Direction Matters More Than a Snapshot
RAG trajectory across the last 1 weekly reporting cycles (2 = Green, 1 = Amber, 0 = Red)
Chart: 
| Wk 1 (July 2)
Titan (Outokumpu) S2P Implementation | 0
UniSan S2P Implementation | 1
Titan (Outokumpu) S2P Implementation — Stable
Trajectory: Red. Held steady across all 1 reporting weeks at Red.
UniSan S2P Implementation — Stable
Trajectory: Amber. Held steady across all 1 reporting weeks at Amber.

## Slide 4
Emerging Risks Across the Portfolio
Patterns that would be missed by reviewing each project in isolation
1
No Significant Cross-Project Risk Patterns Detected
No recurring blockers, correlated overspend, or leading-sentiment patterns were detected across the portfolio this period.

## Slide 5
Spotlight: Titan (Outokumpu) S2P Implementation
STATUS: RED
Schedule
Critical milestone(s) late: Configuration and Build phase, Production & Cutover.
Budget
Budget actuals/planned-to-date not provided — flagged for follow-up.
Milestones
2 milestones are overdue: Configuration and Build phase, Production & Cutover.
Blockers
3 open blockers — escalating volume of unresolved issues.
Sentiment
Stakeholder tone is negative but not escalating.
Bottom line for the client conversation
Critical milestone(s) late: Configuration and Build phase, Production & Cutover. This requires executive-level attention this cycle — Escalate the open blocker(s) to the steering committee this week; they are the primary driver of risk.

## Slide 6
Executive Recommendations
Actions for this coming month, in priority order
1
Address the Titan (Outokumpu) S2P Implementation schedule issue this week
Critical milestone(s) late: Configuration and Build phase, Production & Cutover.

## Slide 7
Appendix: How RAG Status Is Determined
Automated weekly scoring across five weighted signals, with escalation overrides
Schedule (25%)
% of tasks past their planned date; any late critical milestone forces Red.
Budget (20%)
Actual vs. planned spend-to-date. Green 90–110%, Amber 70–90% / 110–130%, Red beyond that.
Milestones (25%)
Overdue milestones and those due within 2 weeks flagged at risk.
Blockers (20%)
Count, severity, and age of open blockers; any critical or 14+ day blocker escalates.
Sentiment (10%)
PM/client narrative tone and week-over-week trend, classified automatically.
Missing data is never treated as automatically Green — it is scored Amber and flagged for follow-up. Critical blockers or 2+ overdue milestones override the weighted score and force Red regardless of other signals.
Full methodology: RAG_METHODOLOGY.md | Agent source: /agent | Weekly reports: /outputs/weekly